## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
My Parking Space |  | 30 | 2021-08-21 | 2020-09-20 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-20 | 2021-08-22 | 2
1.2 | Finish webpage | 2021-08-23 | 2021-08-24 | 1
1.3 | Project Design | 2021-08-24 | 2021-08-27 | 3
2 | Coding
2.1 | Phase 1 | 2021-08-28 | 2021-09-04 | 8
2.2 | Phase 2 | 2021-09-05 | 2021-09-08 | 4
2.3 | Additional Features | 2021-09-09 | 2021-09-10 | 2
3 | Testing
3.1 | Phase 1 Testing | 2021-09-11 | 2021-09-12 | 2
3.2 | Modification /Any changes | 2021-09-13 | 2021-09-13 | 1
3.3 | Phase 2 Testing | 2021-09-14 | 2021-09-15 | 2
3.4 | Modification /Any changes | 2021-09-16 | 2021-09-17 | 2
3.5 | Final Testing | 2021-09-18 | 2021-09-20 | 3
4 | Documentation
4.1 | User Guide | 2021-09-21 | 2021-09-22 | 2
4.2 | Presentation | 2021-09-23 | 2021-09-27 | 5

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Leader
| Member Name | Himanshu Deshpande
| PRN No | 210543181029
Description
2 | Role
| Member Name | Amit Khendake
| PRN No | 210543181042
Description
3 | Role
| Member Name | Akshay Ringe
| PRN No | 210543181006
Description
4 | Role
| Member Name | Sahil Kshirsagar
| PRN No | 210543181046
Description